## Sheet1
APPENDIX :(table(III)) |  |  |  | DRAFT PROGRAMME FOR SSS
[5 empty] | 2017 | [12 empty] | 2018 | [11 empty] | 2019 | [10 empty] | 2020
| JAN | FEB | MAR | APRIL | MAY | JUNE | JULY | AUGUST | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APRIL | MAY | JUNE | JULY | AUGUST | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APRIL | MAY | JUNE | JULY | AUGUST | SEPT | OCT | NOV | DEC | JAN | FEB | APRIL | MAY | JUNE | JULY | AUGUST | SEPT | OCT | NOV | DEC
PART 1 COMPENDIUM SSS (Web based) | FEB: COMPENDIUM PLAN DOCUMENT
PART 2 STATUTORY PLAN | 2017 OCT: STATUTORY PLAN -EVIDENCE SURVEY/ VISION AND OPTIONS/CONSULTATION; 2018 NOV: DRAFT PLAN /CONSULTATION /DEPOSIT VERSION; 2019 OCT: EXAMINATION PROCESS AND I REPORT
OPTION NON STATUTORY PLAN | 2017 OCT: NON STATUTORY PLAN _EVIDENCE SURVEY/VISIONAND OPTIONS/CONSULTATION; 2018 NOV: DRAFT PLAN /CONSULTATION /DEPOSIT VERSION; 2018 MAY: ADOPTION AND BEGIN MOU's; 2020 JULY: WORK COMMENCE ON INDIVIDUAL STATUTORY LOCAL PLANS